## Issues Roster
PFAC Issues Tracker | Initial Date Presented | Presentation Type (E= Educational, F=feedback) | Presenter | Status | Baseline Metrics (from presenter) | Follow Up Date | Action(s) Taken | Follow-Up Metrics (from presenter)
Falls prevention for ABMT patients | 2014-08-15 | F | Loftis J | Kick off meeting held with staff | Avg. # falls per patient/mo.=0.5 | 2014-12-20 | Nurse education re: patient- and family-centered care and falls prevention; cue sheets for nurses | Avg. # falls per patient/mo.=0.25
HCAHPS and Press Ganey overview | 2014-08-15 | E | Turner P | NA | NA | 2014-03-12 | NA | NA
Chemotherapy patient education template and when best to discuss information | 2014-08-15 | F | Griffin T. | Additions made, shared with education governance council for approval | NA | 2014-12-20 | Changes made to education materials related to language
Vericom TV system | 2014-09-12 | F | Thompson K | Put in 2015 budget request | NA | 2015-03-16 | Plan to purchase in FY15
Family presence policy | 2014-09-12 | E | Christensen T | Under revision | NA | 2014-12-20 | Changes made based on feedback
Wait time communication board | 2014-09-12 | F | Boswell A | Will come back to PFAC in Dec. with proposed design. | NA | 2014-12-20 | Standardized board developed for clinics 2, 3, & 5
Chemotherapy education class | 2014-10-15 | F | Johnson H | Will bring feedback to education council and follow-up with PFAC | NA | 2015-03-18 | Looking at developing small video pieces
Discharge follow up telephone call | 2014-11-17 | E/F | Dalton K | Gathering information on types of questions; will return with final product | NA | 2015-01-22 | Feedback and timing incorporated into call protocol
"Why am I Waiting so Long?" document | 2014-12-20 | F | Griffin T | Email sent 8/21 for review by PFAC | NA | 2015-08-21 | Gathered input, will work with K. Butler to improve and bring back.
Radiation patient education slides | 2014-12-20 | F | Dalton K | Will bring suggested revisions back to education council. | NA | 2015-02-16
Patient and Family Brochure: What to Expect on the Day of Surgery |  | E/F
Walk-About: Eye Center Surgical Waiting area (high traffic area, how can we make it more comfortable/less of a transition space?) |  | F
Vending: healthier options |  | F
Initial Scheduling Experience |  | F
Infection control |  | E
Nutrition services |  | E
Patient education-Increase awareness of resources (online, print, video) |  | F
Enhanced online presence and media for education and support (Q&A, Live Chat, Call in Hour, etc.) |  | E/F